## Revision History
Document Revision Control Table
Version No. | Date Revised | Change Description | A/M/D (Add/Modify/Deleted) | Prepared By | Approved By
1 | 2023-10-02 | Performed UAT, Test Executions | Modified | Edward Joseph Santos

## RTM
Requirement Traceability Matrix
Name: Edward Joseph P. Santos | [6 empty] | Date: October 3, 2023
Course/Yr./Sec: BSIT 4GG2 | [6 empty] | Activity 3 - Creating of RTM
Project Name: Dean's Office Transaction
Req ID | Req Desc | Test Case ID | TC Desc | Priority | Input Data | Expected Result | Test Design | Test Designer | UAT Test Req? | Test Execution |  |  | Defect | Defect ID | Defect Status | Req Coverage Status
[10 empty] | Test Env | UAT Env | Prod Env
TSD_000 | Validate Register Account Functionality | REG_001 | Register Button Functionality | High | N/A | User is directed to the registration page where they can create a new account. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REG_002 | Register New Account | High | User provides valid email, password, and personal details | User is successfully registered and redirected to the dashboard page. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REG_003 | Register with Existing Email | Medium | User provides an email that is already registered | User receives an error message indicating that the email is already in use. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REG_004 | Password Strength | High | User provides a weak password | User receives an error message indicating that the password is too weak. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REG_005 | Password Mismatch Check | High | User's password mismatch | User receives an error message indicating that the password does not match. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REG_006 | Missing Required Fields | High | User leaves one or more required fields empty | User receives an error message indicating that all required fields must be filled. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REG_007 | Email Validation | High | User provides an invalid email format | User receives an error message indicating that the email format is invalid. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
TSD_001 | Validate Login Functionality | LOG_001 | Email Validation | High | N/A | User is prompted to sign in with their Google account or select a Google account if they're not already signed in. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | LOG_002 | Google Account Selection | High | N/A | The user is signed in with the selected Google account and redirected to the application. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | LOG_003 | Successful Login | High | Valid username and password | User is successfully logged in and redirected to the dashboard or home page. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | LOG_004 | Incorrect Password | High | Valid username and incorrect password | User receives an error message indicating that the password is incorrect. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | LOG_005 | Non-existent User | Medium | Non-existent username and any password | User receives an error message indicating that the username does not exist. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | LOG_006 | Missing Required Fields | High | Leave one or both fields empty | User receives an error message indicating that all required fields must be filled. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | LOG_007 | Account Lockout | High | Multiple consecutive failed login attempts | User receives an error message indicating that the account is locked due to too many failed attempts. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-LOG_001 | Open | Partial
|  | LOG_008 | Successful Password Reset | High | Valid email | User receives a success message and an email with instructions to reset their password. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-LOG_002 | Open | Partial
|  | LOG_009 | Invalid Email Format | High | Invalid email format | User receives an error message indicating that the email format is invalid. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-LOG_003 | Open | Partial
|  | LOG_010 | Non-existent Email | Medium | Email that doesn't exist | User receives a success message (to prevent email enumeration) but no email is sent. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-LOG_004 | Open | Partial
TSD_002 | Validate Dashboard Functionality | DASH_001 | Logout Button Functionality | High | N/A | The user is successfully logged out from the application. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | DASH_002 | Dashboard Loading | High | N/A | The dashboard loads successfully with all relevant widgets, data, and elements displayed as expected. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | DASH_003 | Widget Functionality | High | N/A | Widgets and modules function correctly, displaying accurate data and responding to user interactions. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | DASH_004 | Data Accuracy | High | N/A | Data in the dashboard is accurate and up-to-date, matching the source or database. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | DASH_005 | Dashboard Responsiveness | High | N/A | The dashboard layout and elements adjust appropriately to different screen sizes without issues. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-DASH_001 | Open | Partial
|  | DASH_006 | Schedule | Medium | N/A | The calendar shows the scheduled dates of incoming and outgoing documents. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | DASH_007 | View Button | High | N/A | The incoming document section will open and the list of uploaded documents is displayed accurately, including document names and upload dates. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-DASH_002 | Open | Partial
TSD_003 | Validate Reports Functionality | REP_001 | Reports Page Loading | High | N/A | The user is successfully logged out from the application. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REP_002 | Report List Display | High | N/A | The dashboard loads successfully with all relevant widgets, data, and elements displayed as expected. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REP_003 | Report Details Display | Medium | N/A | Widgets and modules function correctly, displaying accurate data and responding to user interactions. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REP_004 | Item Restoration | High | Selected deleted item for restoration | Data in the dashboard is accurate and up-to-date, matching the source or database. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | REP_005 | Document Logs | High | N/A | The dashboard layout and elements adjust appropriately to different screen sizes without issues. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
TSD_004 | Validate Incoming Documents Functionality | INC_001 | Document Upload | High | Document files | The selected document files are successfully uploaded and displayed in the Incoming Documents section. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | INC_002 | Document List Display | High | N/A | The list of uploaded documents is displayed accurately, including document names and upload dates. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | INC_003 | Document Preview | High | N/A | The document content is displayed accurately for preview, allowing the user to view its contents. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | INC_004 | Document Print | High | Download all document | The overall document is downloaded successfully to the user's device in the chosen format (e.g., PDF). | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | INC_005 | Document Search | Medium | Search terms or filters | The search or filter functionality works as expected, helping the user find the desired documents. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | INC_006 | Document Deletion | Medium | Selected document for deletion | The selected document is deleted from the system, and it no longer appears in the document list. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | INC_007 | Modify Document Content | Medium | Selected document for modification | The document content is successfully modified, and the changes are saved and reflected in the document. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
TSD_005 | Validate Outgoing Documents Functionality | OUT_001 | Document Upload | High | Document files | The new document is successfully created and displayed in the Outgoing Documents section. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | OUT_002 | Document List Display | High | N/A | The list of created documents is displayed accurately, including document names and creation dates. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | OUT_003 | Document Preview | High | N/A | The document content is displayed accurately for preview, allowing the user to view its contents. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | OUT_004 | Document Print | High | Download all document | The overall document is downloaded successfully to the user's device in the chosen format (e.g., PDF). | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | OUT_005 | Document Search | Medium | Search terms or filters | The search or filter functionality works as expected, helping the user find the desired documents. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | OUT_006 | Document Deletion | Medium | Selected document for deletion | The selected document is deleted from the system, and it no longer appears in the document list. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | OUT_007 | Modify Document Content | Medium | Selected document for modification | The document content is successfully modified, and the changes are saved and reflected in the document. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
TSD_006 | Validate Archiving Documents Functionality | ARC_001 | Document Archiving | High | Document details | The selected document is successfully archived and removed from the active documents list. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | ARC_002 | Document Preview | High | N/A | The document content is displayed accurately for preview, allowing the user to view its contents. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | ARC_003 | Document Print | High | Download all document | The overall document is downloaded successfully to the user's device in the chosen format (e.g., PDF). | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | ARC_004 | Document Search | Medium | Search terms or filters | The search or filter functionality works as expected, helping the user find the desired archived documents. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | ARC_005 | Document Deletion | Medium | Selected archived document for permanent deletion | The selected archived document is permanently deleted from the system and no longer appears in the archives list. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | ARC_006 | Document Restoration from Archives | Medium | Selected archived document for restoration | The selected archived document is successfully restored and moved back to the active documents list. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-ARC_001 | Open | Partial
TSD_007 | Validate Templates Functionality | TEMP_001 | Template Creation | High | Template details | The new template is successfully created and listed in the Templates section. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | TEMP_002 | Template List Display | High | N/A | The list of created templates is displayed accurately, including template names and creation dates. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | TEMP_003 | Template Download | High | Selected template for download | The selected template is downloaded successfully to the user's device in the chosen format (e.g., PDF). | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | TEMP_004 | Template Search | Medium | Search terms or filters | The search or filter functionality works as expected, helping the user find the desired templates. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | TEMP_005 | Template Deletion | Medium | Selected template for deletion | The selected template is deleted from the system, and it no longer appears in the templates list. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
TSD_008 | Validate Archiving Documents Functionality | SET_001 | User Profile Update | High | Updated user profile | The user profile information is successfully updated, and the changes are reflected in the user's account. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-SET_001 | Open | Partial
|  | SET_002 | Theme Selection | High | Selected theme option | The selected theme is successfully applied to the application's user interface. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | SET_003 | Theme Persistence | High | N/A | The currently selected theme is displayed as active, indicating that the user's choice is persisted. | Completed | Edward | Y | Pass | Not Tested | Not Tested | No |  | N/A | Completed
|  | SET_004 | Password Change | High | New and old passwords | The password is successfully changed, and the user is prompted to re-login with the new credentials. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-SET_002 | Open | Partial
|  | SET_005 | Password Mismatch Check | High | Mismatched new passwords | The system detects the password mismatch and displays an error message to the user. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-SET_003 | Open | Partial
|  | SET_006 | Password History Check | Medium | Previously used passwords | The system correctly prevents changing the password to a previously used one and notifies the user. | Completed | Edward | Y | Fail | Not Tested | Not Tested | Yes | DFD-SET_004 | Open | Partial

## Traceability Matrix
Requirement Traceability Matrix
Project Name: CICT Dean's Office Transaction Management System
Functionality Matrix Reference | Application Requirements Definition / Use cases | Module | Requirement Description | Source Code | Unit/Module Test Cases IDs | Release details
TSD_000 | User Account Registration | Registration Module | Allow registration/creation of new account with the user's valid information | deans-office-transaction\src\pages\SignUp.jsx | REG_001:Register Button Functionality | Release Version: 1.0.0
| Existing email address validation |  | Identifies the existing email address | deans-office-transaction\src\pages\SignUp.jsx | REG_002:Register New Account | Release Version: 1.0.0
| Password Strength Verification During User Registration |  | Requiring users to create strong password to enhance security and reduce the risk of unauthorized access. | deans-office-transaction\src\pages\SignUp.jsx | REG_003:Register with Existing Email | Release Version: 1.0.0
| User Password Mismatch Check |  | Implement a password mismatch check within the Registration Module to ensure that users enter their chosen password correctly during the account creation process. | deans-office-transaction\src\pages\SignUp.jsx | REG_004:Password Strength | Release Version: 1.0.0
| Handling Missing Required Fields |  | Identify and prompt users regarding any omitted required fields. | deans-office-transaction\src\pages\SignUp.jsx | REG_005:Password Mismatch Check | Release Version: 1.0.0
| Confirmation email |  | Ensure the accuracy and integrity of provided email addresses | deans-office-transaction\src\pages\SignUp.jsx | REG_006:Missing Required Fields | Release Version: 1.0.0
| Email Validation in Pre-Login Prompt Page |  | Incorporate an email validation process to ensure that users enter a valid and properly formatted email address before proceeding with the login process | deans-office-transaction\src\pages\SignUp.jsx | REG_007:Email Validation | Release Version: 1.0.0
TSD_001 | Google Account Selection for Authentication | Log in Module | The capability for users to select their preferred Google account for authentication throughout the "Sign In with Google" process. | deans-office-transaction\src\pages\Login.jsx | LOG_001:Email Validation | Release Version: 1.0.0
| Successful authentication |  | Allow registered users to successfully log in to their accounts | deans-office-transaction\src\pages\Login.jsx | LOG_002:Google Account Selection | Release Version: 1.0.0
| Handling Incorrect Password during Login |  | Effectively handle scenarios where users provide an incorrect password during the login process | deans-office-transaction\src\pages\Login.jsx | LOG_003:Successful Login | Release Version: 1.0.0
| Handling Non-existent User during Login |  | Handle situations in which individuals attempt to log in with a username/email that does not exist. | deans-office-transaction\src\pages\Login.jsx | LOG_004:Incorrect Password | Release Version: 1.0.0
| Handling Missing Required Fields during Login Registration |  | Effectively handle scenarios where users attempt to log in without providing all the required fields | deans-office-transaction\src\pages\Login.jsx | LOG_005:Non-existent User | Release Version: 1.0.0
| Account Lockout for Security |  | After a certain number of failed login attempts, user accounts are temporarily locked. | deans-office-transaction\src\pages\Login.jsx | LOG_006:Missing Required Fields | Release Version: 1.0.0
| Successful password verification |  | Enable registered users to reset their passwords successfully in the event of a forgotten or compromised password | deans-office-transaction\src\pages\Login.jsx | LOG_007:Account Lockout | Release Version: 1.0.0
| Handling Invalid Email Format in Registration/Login |  | Handle situations in which users attempt to register or log in using an email address that does not follow typical email format norms. | deans-office-transaction\src\pages\Login.jsx | LOG_008:Successful Password Reset | Release Version: 1.0.0
| Handling Non-existent Email in Registration/Login |  | Handle scenarios where users attempt to register or log in with an email address that does not exist in the application's user database. | deans-office-transaction\src\pages\Login.jsx | LOG_009:Invalid Email Format | Release Version: 1.0.0
| Handling Multiple Password Reset Attempts |  | Safeguards to handle scenarios where multiple password reset attempts are made within a defined timeframe. | deans-office-transaction\src\pages\Login.jsx | LOG_010:Non-existent Email | Release Version: 1.0.0
TSD_002 | User Logout | Dashboard | Logging out of the application effectively. | deans-office-transaction\src\pages\Dashboard.jsx | DASH_001:Logout Button Functionality | Release Version: 1.0.0
| Dashboard Loading |  | Shall load and display the user dashboard effectively upon successful user authentication within the dashboard module. | deans-office-transaction\src\pages\Dashboard.jsx | DASH_002:Dashboard Loading | Release Version: 1.0.0
| Widget performance |  | Functional widgets within the user dashboard to allow users to access and interact with specific features and data relevant to their roles. | deans-office-transaction\src\pages\Dashboard.jsx | DASH_003:Widget Functionality | Release Version: 1.0.0
| Ensuring Data Accuracy |  | The accuracy and integrity of data presented within the user dashboard to provide reliable and trustworthy information | deans-office-transaction\src\pages\Dashboard.jsx | DASH_004:Data Accuracy | Release Version: 1.0.0
| Seamless Dashboard |  | Ensure the responsiveness of the user dashboard to provide a seamless and efficient user experience | deans-office-transaction\src\pages\Dashboard.jsx | DASH_005:Dashboard Responsiveness | Release Version: 1.0.0
| Dashboard Scheduling |  | Provide scheduling functionality within the user dashboard, enabling users to create, view, and manage schedules and appointments. | deans-office-transaction\src\pages\Dashboard.jsx | DASH_006:Schedule | Release Version: 1.0.0
| View Document from Dashboard |  | Access and view specific documents associated with the dashboard. | deans-office-transaction\src\pages\Dashboard.jsx | DASH_007:View Document Button | Release Version: 1.0.0
TSD_003 | Loaded Reports page | Reports Module | Ensure that the Reports Page Module loads efficiently and in a timely manner when users access it. | deans-office-transaction\src\pages\Reports.jsx | REP_001:Reports Page Loading | Release Version: 1.0.0
| Display Reports List |  | View and access a comprehensive list of reports that are available for them to run or review. | deans-office-transaction\src\pages\Reports.jsx | REP_002:Report List Display | Release Version: 1.0.0
| Display Report Details |  | Provide detailed information for each report listed in the user dashboard, allowing users to access comprehensive details about specific reports. | deans-office-transaction\src\pages\Reports.jsx | REP_003:Report Details Display | Release Version: 1.0.0
| Document Log Management |  | Provide a detailed record of document-related activities and interactions | deans-office-transaction\src\pages\Reports.jsx | REP_004:Item Restoration | Release Version: 1.0.0
| Document Upload |  | Provide a detailed record of document-related activities and interactions | deans-office-transaction\src\pages\Reports.jsx | REP_005:Document Logs | Release Version: 1.0.0
TSD_004 | Upload Incoming Document | Incoming Documents Module | Upload and manage incoming documents ensuring that all relevant documents are securely stored and accessible. | deans-office-transaction\src\pages\IncomingTable.jsx | INC_001:Document Upload | Release Version: 1.0.0
| Display Incoming Document List |  | Allows users to view and manage documents received from external sources. | deans-office-transaction\src\pages\IncomingTable.jsx | INC_002:Document List Display | Release Version: 1.0.0
| Preview selected Documents |  | Quickly review document contents without the need to download or open the document in a separate application. | deans-office-transaction\src\pages\IncomingTable.jsx | INC_003:Document Preview | Release Version: 1.0.0
| Print incoming documents |  | Capability to print incoming documents from within the Incoming Documents module, allowing for hard-copy output when necessary. | deans-office-transaction\src\pages\IncomingTable.jsx | INC_004:Document Print | Release Version: 1.0.0
| Search Incoming Documents |  | Robust document search capability within the Incoming Documents module, enabling them to quickly locate specific documents | deans-office-transaction\src\pages\IncomingTable.jsx | INC_005:Document Search | Release Version: 1.0.0
| Delete documents |  | Allows them to manage their document repository by removing unwanted or obsolete documents. | deans-office-transaction\src\pages\IncomingTable.jsx | INC_006:Document Deletion | Release Version: 1.0.0
| Modify specific documents. |  | Modify the content of documents within the Incoming Documents module, allowing for necessary updates, corrections, or annotations to document content. | deans-office-transaction\src\pages\IncomingTable.jsx | INC_007:Modify Document Content | Release Version: 1.0.0
TSD_005 | Upload Outgoing Document | Outgoing Documents Module | Upload and manage outbound documents ensuring that all relevant documents are securely stored and accessible. it streamlines the process of capturing and organizing important documents, ensuring they are accessible and securely stored within the application. | deans-office-transaction\src\pages\OutgoingTable.jsx | OUT_001:Document Upload | Release Version: 1.0.0
| Display Outgoing Document List |  | Allows users to view and manage documents received from external sources. | deans-office-transaction\src\pages\OutgoingTable.jsx | OUT_002:Document List Display | Release Version: 1.0.0
| Preview Outgoing Documents |  | Allows user to quickly assess document content before finalizing and sending documents. | deans-office-transaction\src\pages\OutgoingTable.jsx | OUT_003:Document Preview | Release Version: 1.0.0
| Print Outgoing Documents |  | Capability to print outgoing documents from within the Outgoing Documents module, allowing for hard-copy output when necessary. | deans-office-transaction\src\pages\OutgoingTable.jsx | OUT_004:Document Print | Release Version: 1.0.0
| Search Outgoing Documents |  | Robust document search capability within the Outgoing Documents module, enabling them to quickly locate specific documents based on various criteria. | deans-office-transaction\src\pages\OutgoingTable.jsx | OUT_005:Document Search | Release Version: 1.0.0
| Outgoing Document Deletion |  | Capability to delete documents from within the Outgoing Documents module, allowing them to manage their document repository by removing unwanted or obsolete documents. | deans-office-transaction\src\pages\OutgoingTable.jsx | OUT_006:Document Deletion | Release Version: 1.0.0
| Modify Outgoing document Content |  | Capability to modify the content of outgoing documents within the Outgoing Documents module, allowing for necessary updates, corrections, or annotations to document content. | deans-office-transaction\src\pages\OutgoingTable.jsx | OUT_007:Modify Document Content | Release Version: 1.0.0
TSD_006 | Archive Documents | Archive Module | Allows users to organized storage and retrieval of historical documents. | deans-office-transaction\src\pages\ArchiveTable.jsx | ARC_001:Document Archiving | Release Version: 1.0.0
| Document Preview in Archive Module |  | Allowing them to view the content of archived documents without fully restoring them. | deans-office-transaction\src\pages\ArchiveTable.jsx | ARC_002:Document Preview | Release Version: 1.0.0
| Document Printing in Archive Module |  | Allows users to produce hard copies of archived documents when needed. | deans-office-transaction\src\pages\ArchiveTable.jsx | ARC_003:Document Print | Release Version: 1.0.0
| Document Search in Archive Module |  | Advanced search capabilities within the Archive Module, allowing them to efficiently locate archived documents based on various criteria. | deans-office-transaction\src\pages\ArchiveTable.jsx | ARC_004:Document Search | Release Version: 1.0.0
| Document Deletion in Archive Module |  | Allows users to manage their archived document repository by removing unwanted or obsolete documents. | deans-office-transaction\src\pages\ArchiveTable.jsx | ARC_005:Document Deletion | Release Version: 1.0.0
| Document Restoration from Archives |  | Allows user to recover documents that were previously deleted. | deans-office-transaction\src\pages\ArchiveTable.jsx | ARC_006:Document Restoration from Archives | Release Version: 1.0.0
TSD_007 | Create Template | Template Module | Capability to create templates within the Template Module, allowing them to design and store document templates for future use. | deans-office-transaction\src\pages\TemplatesTable.jsx | TEMP_001:Template Creation | Release Version: 1.0.0
| Display list of templates |  | Provide users with a comprehensive list display of templates, allows the users to view and select templates for document creation or editing. | deans-office-transaction\src\pages\TemplatesTable.jsx | TEMP_002:Template List Display | Release Version: 1.0.0
| Download templates |  | Capability to download templates, allows users to save templates locally for offline use or further customization. | deans-office-transaction\src\pages\TemplatesTable.jsx | TEMP_003:Template Download | Release Version: 1.0.0
| Seacrh Template |  | Advanced search capabilities allowing users to efficiently locate templates based on various criteria. | deans-office-transaction\src\pages\TemplatesTable.jsx | TEMP_004:Template Search | Release Version: 1.0.0
| Delete Template |  | Capability to delete templates to manage their template repository by removing unwanted or obsolete templates. | deans-office-transaction\src\pages\TemplatesTable.jsx | TEMP_005:Template Deletion | Release Version: 1.0.0
TSD_008 | Updated User Profile information | Settings Module | Capability to update their user profiles to modify their personal information and preferences. | deans-office-transaction\src\pages\Settings.jsx | SET_001:User Profile Update | Release Version: 1.0.0
| Modified Theme |  | Select and customize application themes, and personalize the appearance and user experience | deans-office-transaction\src\pages\Settings.jsx | SET_002:Theme Selection | Release Version: 1.0.0
| Continuity of Theme |  | Persistence of selected or customized themes, allowing users to have their preferred theme applied consistently across application sessions. | deans-office-transaction\src\pages\Settings.jsx | SET_003:Theme Persistence | Release Version: 1.0.0
| User Account Password change |  | Capability to change their account password securely to enhance the security of their accounts. | deans-office-transaction\src\pages\Settings.jsx | SET_004:Password Change | Release Version: 1.0.0
| Password mismatch confirmation |  | To ensure that users correctly confirm their new passwords during the password change process. | deans-office-transaction\src\pages\Settings.jsx | SET_005:Password Mismatch Check | Release Version: 1.0.0
| Password History |  | Prevent users from reusing their recent passwords when changing their account passwords. | deans-office-transaction\src\pages\Settings.jsx | SET_006:Password History Check | Release Version: 1.0.0